## Overview
プロジェクト： | 在庫管理システム
【概要】
本システムは、小規模コンビニの在庫を管理・モニタリングするためのシステムである。
本プロジェクトのスコープ（実施すべき機能）につきましては、下記のユーズケース図へ参照。
ユースケース図
【要件定義】
A）機能要件 | 下記の一覧表に機能の記述・優先度を示す。
| 優先度 | 項目（機能要件） | 記述・受け入れ基準
| 1 | Add Inventory Item | As a staff, I can add an item to the inventory in such a way that I can still distinguish each batch of products even if they have the same item description.
| 2 | Update Inventory Item | As a staff, I can correct any details of an existing item in the inventory.
| 3 | View Inventory List | As a staff, I can view all the items in the inventory, sorted by item ID.
| 4 | Search for an Inventory Item | As a staff, I can search the inventory if a particular item ID or product exists.
| 5 | Delete Inventory Item | As a staff, I can delete a specific existing item in the inventory. (This will mainly be used only to delete erroneously inputted entries.)
B）非機能要件 | 下記の一覧表に非機能の優先度を明確に示す。
| 優先度 | 項目（非機能要件） | 詳細
| 1 | 相互運用性 (Interoperability) | The inventory list must be in CSV format, so that it will be easy to utilize the data as input to other systems being used by the small-scale convenience store.
| 2 | 性能性 (Performance) | Response time for all major functionalities of the system should be within 1 second.
| 3 | 使いやさ (Usability) | The system must be easy-to-use, easy to understand, and easy to operate/control.

## Q&A
# |  | Topic | Question | Date Asked | Asked by | Answer | Date Answered | Answered by
| 1 | Definition | Datatypes, range, and length rules for the System: ID: CHAR[6], 5 digits + terminator, numerical, range (00000-99999) Description: CHAR[41], 40 characters + terminator, Alphanumeric, cannot be blank Quantity: INT, 4 digits, numerical, range (0-4999), unsigned Expiration date: CHAR[11], numerical/'-', Can only be either a dash(-) for items with no expiry or a date input with format yyyy-mm-dd Price: FLOAT, numerical with decimal, range (0.0-99999.99), unsigned | 2021-10-27 | J. Bandong | ID: using either int or char[6] would be a design decision (int is 4 bytes, char[6] is 6 bytes). However, on the part of the staff, it would be easier to see if the ID has a fixed length of 5 digits when displayed on screen or when viewed in the CSV file. Description: please recheck the length with the layout for the View Inventory List Quantity: please qualify whether the data type is signed or unsigned Expiration Date: OK. So this will be char[11] (11 bytes; 10 bytes for the characters in the date + '\0' for the end-of-string/null terminator) Price: float would be more space-efficient -- float is 4 bytes whereas double is 8 bytes. The price also does not need to have that level of precision in a double (because we only represent 2 decimal places for PHP currency). | 2021-10-27 | R. Rodriguez
| 2 | Assumptions | Error Handling with non-existent file. System will check for file on start and on every function call if the file exists or not. If the file exists, continue with the program. If file does not exist, System will create a new file with the file name "Inventory.csv" | 2021-10-27 | J. Bandong | Yes, you may proceed with this assumption. | 2021-10-27 | R. Rodriguez
| 3 | Assumptions | FIle can only be used by the system. Contents cannot be changed externally. | 2021-10-26 | J. Bandong | In actual operations, this can not be guaranteed. It might be the case that a staff would double-click on the CSV file, have it opened in Excel, then accidentally saved it in Excel, potentially changing some values due to autoformatting options in Excel. But anyhow, in my system testing & acceptance testing, I will just set this kind of scenario as a low priority test case. I will focus more on testing the business case scenarios. | 2021-10-26 | R. Rodriguez
| 4 | Assumptions | Inventory items ID, sorted in ascending order EDIT: Not sorted, Add function appends to file | 2021-10-26 | J. Bandong | This would also depend on the details of how you implement the system. If (for example) Add New Inventory Item feature will just append the new entry at the end of the file, then this assumption would not be valid. | 2021-10-26 | R. Rodriguez
| 5 | Assumptions | If there is an invalid input on the Inventory Item, i.e. nothing was inputted as the item's ID, the item would not be listed in the inventory file and an error message would appear. | 2021-10-26 | J. Andicoy | Just to paraphrase the assumption: Context/use case being talked about: Add New Inventory Item ID input value: (blank) Input values for the other fields: (valid values) Expected behavior: The system displays an error message and the inputted item is not added into the inventory. Is my understanding about the assumption correct? If that is the context of the assumption, then yes, we are expecting the same behavior to happen. | 2021-10-26 | R. Rodriguez
| 6 | Assumptions | Searching for the actual name of the product instead of it's ID number. | 2021-10-27 | JM. Marquita | If you can only implement 1 of the 2, the priority is to search for the ID number instead of searching for the product description. Searching for the product description would result to multiple matches, and would mean that the staff would have to type/do more work in the system in order to find a particular item. | 2021-10-27 | R. Rodriguez

## Screen Design
Screen Design
Screen Name: Main Menu
Author(s): R. Rodriguez
.........1.........2.........3.........4.........5.........6.........7.........8
12345678901234567890123456789012345678901234567890123456789012345678901234567890
1 | MAIN MENU
2 | [A] Add Inventory Item
3 | [B] Update Inventory Item
4 | [C] View Inventory List
[D] Search Inventory List
5 | [E] Delete Inventory Item
6 | [X] Exit Program
7
8 | Please input choice: A
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Legend: Text in black color are system-generated outputs; text in red color are sample user input.
| Screen Name: Add Inventory Item (Successful) | Screen Name: Add Inventory Item (Error-3b) | Screen Name: Add Inventory Item (Error-4b)
| Author(s): J. Andicoy | Author(s): J. Andicoy | Author(s): J. Andicoy
| .........1.........2.........3.........4.........5.........6.........7.........8 | .........1.........2.........3.........4.........5.........6.........7.........8 | .........1.........2.........3.........4.........5.........6.........7.........8
| 12345678901234567890123456789012345678901234567890123456789012345678901234567890 | 12345678901234567890123456789012345678901234567890123456789012345678901234567890 | 12345678901234567890123456789012345678901234567890123456789012345678901234567890
| MAIN MENU | MAIN MENU | MAIN MENU
| [A] Add Inventory Item | [A] Add Inventory Item | [A] Add Inventory Item
| [B] Update Inventory Item | [B] Update Inventory Item | [B] Update Inventory Item
| [C] View Inventory List | [C] View Inventory List | [C] View Inventory List
| [D] Delete Inventory Item | [D] Delete Inventory Item | [D] Delete Inventory Item
| [X] Exit Program | [X] Exit Program | [X] Exit Program
| Please input choice: A | Please input choice: A | Please input choice: A
| Please input Item ID: 11155 | Please input Item ID: 11155 | Please input Item ID: 11155
| Please input Item Description: Potchi | Please input Item Description: Potchi | Please input Item Description: Potchi
| Please input Item Quantity: 50 | Please input Item Quantity: 50 | Please input Item Quantity: 50
| Please input Item Expiry Date | Please input Item Expiry Date | Please input Item Expiry Date
| Year: 2020 | Year: 2020 | Year: 2020
| Month: 12 | Month: 15 | Month: 12
| Date: 22 | Date: 22 | Date: 22
| Please input Price: 2.00 | Please input Price: 2.00 | Please input Price: 2.00
| ...... | ...... | ......
| ...... | ...... | ......
| Success! Inventory Item has been added! | Error! Invalid Input! Inventory Item has not been added! | Error! ID Already Exists! Inventory Item has not been added!
| Legend: Text in black color are system-generated outputs; text in red color are sample user input. | Legend: Text in black color are system-generated outputs; text in red color are sample user input. | Legend: Text in black color are system-generated outputs; text in red color are sample user input.
Screen Name: Update Inventory Item
Author(s): J. Bandong
.........1.........2.........3.........4.........5.........6.........7.........8
12345678901234567890123456789012345678901234567890123456789012345678901234567890
| Update Inventory Item | Update Inventory Item | Update Inventory Item
| Please input Item ID to Update: 11101 | Please input Item ID to Update: 11101 | Please input Item ID to Update: 10001
| Please input Item Description: Nat. Spring (250mL) | Please input Item Description: Nat. Spring (250mL) | Item ID not found! Returning to Main Menu
| Please input Quantity: 210 | Please input Quantity: 210
| Please input Expiration Date: - | Please input Expiration Date: AAAAAAAA | MAIN MENU
| Please input Price: 8.00 | Please input Price: 8.00 | [A] Add Inventory Item
[B] Update Inventory Item
|  | ONE INPUT IS INVALID! PLEASE TRY AGAIN | [C] View Inventory List
[D] Delete Inventory Item
| Item Updated! | Please input Item Description: Nat. Spring (250mL) | [X] Exit Program
Please input Quantity: 210
Please input Expiration Date: 2023-01-01
Please input Price: 8.00
Item Updated!
MAIN MENU
[A] Add Inventory Item
[B] Update Inventory Item
[C] View Inventory List
[D] Delete Inventory Item
[X] Exit Program
Legend: Text in black color are system-generated outputs; text in red color are sample user input.
Screen Name: View Inventory List
Author(s): I. Paquibulan
.........1.........2.........3.........4.........5.........6.........7.........8
12345678901234567890123456789012345678901234567890123456789012345678901234567890
View Inventory List
INVENTORY LIST
ID : 11101
Description : Nat. Spring (500mL)
Quantity : 200
Expiry Date : -
Price : 10.50
-------------------------------------------------------------
ID : 11201
Description : Nat. Spring (1L)
Quantity : 300
Expiry Date : -
Price : 16.00
-------------------------------------------------------------
[A] Search for an Inventory Item
[X] Return to Main Menu
Legend: Text in black color are system-generated outputs; text in red color are sample user input.
Screen Name: Search for an Inventory Item
Author(s): JM. Marquita
.........1.........2.........3.........4.........5.........6.........7.........8
12345678901234567890123456789012345678901234567890123456789012345678901234567890
| Search for an Inventory Item | Search for an Inventory Item | Search for an Inventory Item
| Please choose: | Please input Item ID to Search: 11101 | Please input Item ID to Search: QWERTY
A - Search using item ID
| B - Search using product name | Sorry, the Item you entered doesn't exist. | Sorry, the Item you entered IS NOT VALID.
|  | Please try another Item ID. | Please try another Item ID.
Enter Answer: A
|  | [D] Search Inventory List | [D] Search Inventory List
| Please input Item ID to Search: 11101 | [R} Return to Menu | [R} Return to Menu
This is the information related to Item 11101:
ID: 11101
Description: Nat. Spring (500mL)
Quantity: 210
Expiry Date: -
Price: 8.00
[D] Search Inventory List
[R} Return to Menu
---------------------------------------------------------------------------------------------
Legend: Text in black color are system-generated outputs; text in red color are sample user input.
| Screen Name: Delete Inventory Item | Screen Name: Delete Inventory Item
| Author(s): R. Manlangit Jr | Author(s): R. Manlangit Jr
| .........1.........2.........3.........4.........5.........6.........7.........8 | .........1.........2.........3.........4.........5.........6.........7.........8
| 12345678901234567890123456789012345678901234567890123456789012345678901234567890 | 12345678901234567890123456789012345678901234567890123456789012345678901234567890
| Delete Item from Inventory | Delete Item from Inventory
| Please input Item ID to delete from Inventory List: 11101 | Please input Item ID to delete from Inventory List: 11101
| "11101","Nat. Spring (500mL)","200","-","10.50" | "11101","Nat. Spring (500mL)","200","-","10.50"
| Are you sure you want to delete this item? Y/N?: Y | Are you sure you want to delete this item? Y/N?: Y
| The Item "11101","Nat. Spring (500mL)","200","-","10.50" has been deleted from the inventory. | The Item "11101","Nat. Spring (500mL)","200","-","10.50" has been deleted from the inventory.
| [R] Return to Main Menu: | [R] Return to Main Menu:
| [E] Delete Inventory Item: | [E] Delete Inventory Item:
| E | R
// invalid ID number
| Please input Item ID to delete from Inventory List: 1110A | MAIN MENU
| The inputted ID is not valid. | [A] Add Inventory Item
| Would you like to delete another item? Y/N?: Y | [B] Update Inventory Item
| Please input Item ID to delete from Inventory List: 11101 | [C] View Inventory List
| "11101","Nat. Spring (500mL)","200","-","10.50" | [D] Search Inventory List
| Are you sure you want to delete this item? Y/N?: N | [E] Delete Inventory Item
E
| Please input Item ID to delete from Inventory List: 11101 | // Non-existing ID number:
...
| ... | Please input Item ID to delete from Inventory List: 11102
| ... | The inputted ID does not exists.
Would you like to delete another item? Y/N?: Y
| [R] Return to Main Menu: | Please input Item ID to delete from Inventory List: 11101
| [E] Delete Inventory Item: | "11101","Nat. Spring (500mL)","200","-","10.50"
Are you sure you want to delete this item? Y/N?: N
Please input Item ID to delete from Inventory List: 11101
| Legend: Text in black color are system-generated outputs; text in red color are sample user input. | ...
...
...
[R] Return to Main Menu:
[E] Delete Inventory Item:

## Bug Reports
Defect/Bug Reports
Bug # | Reported by | Report Date | Summary | Details | Severity | Assigned to | Priority | Status | Notes
1 | R. Rodriguez | 2021-10-26 | Flowchart process "Do not add file into inventory list" | UCD > Add Inventory Item flowchart: There is no need to indicate the "Do not add file into inventory list" as it is not an action that is going to be done by the system. The flow may proceed to displaying the corresponding error message. | Low | J.Andicoy | Low | Fixed
2 | R. Rodriguez | 2021-10-26 | Main success flow for Update Inventory Item | Won't the system show the details of the existing ID that has been inputted by the staff before asking for the new details for the inventory item? (There is a risk that the staff mistyped the ID that is inteded to be updated/corrected.) | High | J.Bandong | Medium | Fixed
3 | R. Rodriguez | 2021-10-26 | Behavior of the system when the inventory CSV file does not exist | What is the expected behavior of the system in the case that the inventory CSV file where add/update/view/search/delete will be done, does not exist? | BugOrNot? | J. Bandong | High | Closed | Indicated in Q&A #2 10/27 [Ryan] Assumption in Q&A #2 is acknowledged. | RA
4 | R. Rodriguez | 2021-10-26 | Maximum character lengths for different fields | How long are the strings/digits for the different fields for an inventory item? (Context/intent of asking the question is to evaluate if 1 entry can really fit in one row on the terminal, which normally has max length of 80-characters) Screen Design > View Inventory List -- is the text for the Description, center-aligned? (Center alignment from column 7 to 37) | Question | J.Bandong | Low | Fixed | Indicated in Q&A #1 10/27 [Ryan] Please reassess either the max length for Description, or the screen design layout for showing the inventory items (such as in View Inventory List) 10/29 [J. Bandong] Changed View Inventory List Screen Design
5 | R. Rodriguez | 2021-10-26 | Missing integration testing test case for Search for an Inventory Item | Integration Testing > The alternate flow for INV-UC-04 that executes Step 5b (i.e., searching another inventory item after having previously searched one inventory item) has not been listed as a test case. | Medium | JM. Marquita | Medium | Fixed
6 | J.Bandong | 2021-10-28 | Feature: Update Test Case: 4 Entering empty string into description field creates a new line. stdin, does not accept empty string | Update Feature > Inputing an empty string in stdin for the Description Field only creates a new line on the terminal. Only when entering characters will the stdin accept the user input | Medium | J.Bandong | Medium | Reject
7 | R. Manlangit | 2021-10-28 | Feature: Delete Entering unstored string displaying cache details of that string | Deleting > System continues to display cache of the deleted data | High | R. Manlangit | High | Fixed | Bug Fix Commit: ebed65b424c791924c1a99bfcba33f1764859744
8 | J.Bandong | 2021-10-28 | Feature: Update Test Case: 14, 15, 17, 18 Input values outside boundaries still accepted by system | System continues to accept input values outside of range indicated by specifications (Q&A: Assumption#1) | Low | J.Bandong | Low | Fixed | Bug Fix Commit: e494555b29e00f2bede883a369891bda4c7e6f68
9 | I. Paquibulan | 2021-10-28 | Feature: View Test Case: 5 Wrong format of Expiry date still accepted by the system | View > System continue to display correct file format in the Expiry date. | Low | I.Paquibulan | Low | Fixed | Bug Fix Commit: 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
11 | J. Andicoy | 2021-10-28 | Feature: Add Test Case: 9 | Adding > System continues to add an item of negative quantity. | Low | J. Andicoy | Low | Fixed | Bug Fix Commit: c4b2143e6a18220d448de1ce5f9805460b4289c5
12 | JM. Marquita | 2021-10-28 | Feature: Search Entering a a string of characters instead of integers is not classified as invalid input. | Searching > The system considered the string of character's as valid inputs and check if it's on the list. But, originally it must be considered as invalid once the user entered it on the system. | Low | JM. Marquita | High | Fixed | Bug Fix Commit: 613ed45400d04a53939800e91399fdccf736a8aa
13 | JM. Marquita | 2021-10-28 | Feature: Search Choosing the "Search again" option directs user to main menu. | Searching> After the searching is complete. The system will ask the user if he/she wants to [1] "Search again" or [2] "Return to Main Menu". Upon choosing option 1, the system go back to the Main Menu. | Low | JM. Marquita | High | Fixed | Bug Fix Commit: ad7a2514bae77110c87d668215cd757fb14fb55c
14 | JM. Marquita | 2021-10-29 | Feature: Search Unit Test Test Case: 7 | Searching > The system let a mixture of integer and character input to pass through, instead of blocking it earlier in the code, | Low | JM. Marquita | High | Fixed | Bug Fixed Commit: 38788b0b84625814da86c9ad0c0ce31922ed04a7
15 | J. Andicoy | 2021-10-29 | Feature: Add Test Case: 17 | Adding > System does not accept input of YYYY-MM-DD if dash. | Low | J. Andicoy | Low | Fixed | Bug Fixed Commit: be54fb49286b669e152ed8a5622a5e9acc2d68cd
16 | JM. Marquita | 2021-10-29 | Feature: Search Integration Test Case: INV-IT-04-04 | Searching > The system let a mixture of integer and character input to pass through, instead of blocking it earlier in the code. | Low | JM. Marquita | Low | Fixed | Bug Fixed Commit: 553d64dafad7b47e5f3505a65e062983f325b6f1
17 | J. Andicoy | 2021-10-29 | Feature: Add Integration Test Case: INV-IT-01-03 | Adding > The system still accepts an item even if an item in the inventory has the same product ID. | Medium | J.Andicoy | High | Fixed | Bug Fixed Commit: 895c4054174aa22f16033bc3382b6ecefa5ff724
18 | J. Bandong | 2021-11-01 | Feature: Update Integration TestCase: INV-IT-02-01 | Updating > System will not save to the file if the item is at the end of the list | High | J. Bandong | High | Fixed | Bug Fixed Commit: 620ce3f807fa468d75cc35a25b7dfa45b0b79fe1
19 | J.Bandong | 2021-11-01 | Feature: Update Integration TestCase: INV-IT-02-01 | Updating > System will read into an empty lines at the end of the inventory list if there is one and will copy values of the last line into it after update | Low | J. Bandong | Low | Accept
20 | R. Manlangit | 2021-11-01 | Feature: View Viewing elements that is not being inputted in the system | View > System will display data that is not being inputted | Low | J. Bandong | Low | Fixed | Bug Fix Commit: 602842e596c6a80ecee344e7b2b2a25fb53a0564
21 | R. Manlangit | 2021-11-01 | Feature: Delete Unable to delete the first row in the csv file | Delete > Whenever you try to delete the data that is in the first row of the inventory.csv the system will shutdown and the data in the first row still remains. | Medium | J. Bandong | Low | Fixed | Bug Fix Commit: 425c8a73c568f8c6345b726c89576fd376a477c1
22 | R. Manlangit | 2021-11-01 | Feature: Add Added Expiration date is not the same in the data registered in the csv file | Add > Whenever you input an expiration date data, only the date is the one that is being registered in the csv file | Medium | J. Bandong | Low | Fixed | Bug Fix Commit: 602842e596c6a80ecee344e7b2b2a25fb53a0564
23 | R. Manlangit | 2021-11-01 | Feature: Add Expiration date month's limit is not set | Adding Expiration date> It cannot filter the month's specific number of dates. For it still accepts the date 31 for the month of February (2), April(4), June(6), September(9), November(11). | Low | J. Andicoy | Low
24 | R. Manlangit | 2021-11-01 | Feature: Delete Incorrect input in return produces a loop | Delete Return / Main Menu > Wrong input of characters in the return main menu / re enter id number will produce a loop and will make the system unfunctionable. Unabling to enter again another input and forcing you to close the program. | Medium | R. Manlangit | Low | Fixed | Bug Fix Commint: 6dfaa2ae8233b5cee0443a8c67a190adceadd24d

## UCD
Use Case Descriptions
Use Case ID |  | INV-UC-01
Use Case Name |  | Add Inventory Item
Author: |  | J. Andicoy
Date Last Updated: |  | 2021-10-25
Reference |  | ユースケース図
Description |  | As a staff, I can add an item to the inventory in such a way that I can still distinguish each batch of products even if they have the same item description.
Primary Actors |  | Staff
Secondary Actors |  | None
Triggers |  | Staff chooses to add a new item in the inventory.
Pre-Conditions |  | Inventory file exists
Success Post-Condition |  | New item inputted by the staff is added to the inventory file
Failure Post-Condition |  | Staff is informed by the system that the item is not added to the inventory file
MAIN SUCCESS SCENARIO
Step # | Action
1 | The staff inputs inventory item details (i.e., ID, Description, Quantity, Expiry Date, Price).
2 | The system checks if the values inputted are valid.
3 | If all inputs are valid, the system checks if the ID already exists in the file.
4 | If the ID does not exist, the system adds the new inventory item as an entry into the inventory file.
5 | The system informs the staff that the inventory item has been added into the inventory file.
ALTERNATIVE FLOWS
Step # | Action
3b | The system informs the staff that the item is not added to the inventory file because of an invalid input.
4b | The system informs the staff that the item is not added to the inventory file because the ID already exists.
Use Case ID |  | INV-UC-02
Use Case Name |  | Update Inventory Item
Author: |  | J. Bandong
Date Last Updated: |  | 2021-10-25
Reference |  | ユースケース図
Description |  | As a staff, I can update an item from the inventory.
Primary Actors |  | Staff
Secondary Actors |  | None
Triggers |  | Staff chooses to update an item in the inventory.
Pre-Conditions |  | Inventory file exists, Item ID exists
Success Post-Condition |  | Item details inputted by the staff is update in the inventory file
Failure Post-Condition |  | Staff is informed by the system that the item is not updated in the inventory file
MAIN SUCCESS SCENARIO
Step # | Action
1 | The staff inputs inventory item ID to be updated.
2 | If the item ID exists in the file, the system will show the details of the item.
3 | The system will prompt if the staff wants to continue with the update,
4 | If continued, the staff inputs inventory item details to be updated (i.e., Description, Quantity, Expiry Date, Price).
5 | The system checks if the values inputted are valid.
6 | If all inputs are valid, the system updates the inventory item in the file.
7 | The system informs the staff that the inventory item has been updated in the inventory file.
ALTERNATIVE FLOWS
Step # | Action
1b | The system informs the staff that the item ID does not exist.
3b | If not continued, the system will go to Main Menu
6b | The system informs the staff that the input is invalid and asks for the details again.
Use Case ID |  | INV-UC-03
Use Case Name |  | View Inventory List
Author: |  | I. Paquibulan
Date Last Updated: |  | 2021-10-25
Reference |  | ユースケース図
Description |  | As a staff, I can view all the items in the inventory, sorted by item ID.
Primary Actors |  | Staff
Secondary Actors |  | None
Triggers |  | Staff chooses to view items in the inventory list.
Pre-Conditions |  | All items are listed in the inventory.
Success Post-Condition |  | All items are viewed by the staff in the inventory list.
Failure Post-Condition |  | Staff is informed by the system that the item is not located in the inventory file
MAIN SUCCESS SCENARIO
Step # | Action
1 | The staff wishes to see the Inventory List from the main menu.
2 | The system will proceed to the inventory list.
ALTERNATIVE FLOWS
Step # | Action
1b | The system informs the staff that the ID is wrong or invalid.
Use Case ID |  | INV-UC-04
Use Case Name |  | Search for an Inventory Item
Author: |  | JM. Marquita
Date Last Updated: |  | 2021-10-25
Reference |  | ユースケース図
Description |  | As a staff, I can search the inventory if a particular item ID or product exists.
Primary Actors |  | Staff
Secondary Actors |  | None
Triggers |  | The Staff decides to search for the item ID or product existence.
Pre-Conditions |  | Inventory file exist
Success Post-Condition |  | The system will tell the staff of the item ID or product information.
Failure Post-Condition |  | The system can't give the product information.
MAIN SUCCESS SCENARIO
Step # | Action
1 | The staff inputs item ID.
2 | The system checks if the input are valid.
3 | If all inputs are valid, the system checks if the item ID already exists in the file.
4 | If the item ID is listed, the system will tell the staff it's information.
5 | The system will tell the staff if he/she wants to search for another Item or go back to main menu.
ALTERNATIVE FLOWS
Step # | Action
3b | The system informs the staff that the item is not valid.
4b | The system informs the staff that the item doesn't exist in the inventory file.
5d | Return to step 1 or to the Main menu
Use Case ID |  | INV-UC-05
Use Case Name |  | Delete an Inventory Item
Author: |  | R. Manlangit Jr
Date Last Updated: |  | 2021-10-25
Reference |  | ユースケース図
Description |  | As a staff, I can delete a specific existing item in the inventory. (This will mainly be used only to delete erroneously inputted entries.)
Primary Actors |  | Staff
Secondary Actors |  | None
Triggers |  | Staff chooses to delete an existing item in the inventory.
Pre-Conditions |  | Inventory file does not exists
Success Post-Condition |  | Existing item ID number inputted by the staff is deleted from the inventory file together with its Description, Quantity, Expiry Date, Price.
Failure Post-Condition |  | Staff is informed by the system that the item is not deleted to the inventory file
MAIN SUCCESS SCENARIO
Step # | Action
1 | The staff inputs inventory ID number.
2 | The system checks if the ID number inputted are valid.
3 | If ID number inputs are valid, the system checks if the ID number is in the file.
4 | If the ID number exist, the system will display the information of the inputted ID number details, and will ask the staff if he wants proceed to the deletion of the inventory file from the system
5 | The system informs the staff that the inventory item has been deleted from the inventory file.
6 | The system will prompt the staff if he/she wants to return to main menu, or delete another item
7 | The system will return to step # 1
ALTERNATIVE FLOWS
Step # | Action
3b | The system informs the staff that the inputted ID number is invalid and will prompt the staff if he/she wants to input another ID or return to main menu
3b1 | The system will return to step # 1
3b2 | The system will return to main menu
4b | The system informs the staff that the item does not exists in the inventory and will prompt the staff if he/she wants to input another ID
4c | The system will return to step # 1
6b | The system will return to step # 1
7b | The system will return to main menu

## Unit Testing
Unit Testing Test Cases
Test procedure: | 1) Execute XXX function with the values for aaa, ..., and jjj indicated in the test cases below.
2) Check the values of xxx, ..., and zzz after executing the XXX function if it matches with the Expected Output.
Test Case | Test Technique |  |  |  |  | INPUT |  |  |  |  | EXPECTED OUTPUT |  |  |  |  | ACTUAL OUTPUT |  |  |  |  | PASS/FAIL |  | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | ID | DESCR | QTY | EXPIRY | PRICE | var1 | var2 | var3 | var4 | var5 | var1 |  | var3 | var4 | var5
<Add Inventory Item>
1 | O |  |  |  | O | 11155 | Potchi | 50 | 2021-10-25 | 5 | T | T | T | T | T | T | T | T | T | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
2 | O |  |  |  |  | 11155 | Potchi | 50 | 2021-13-25 | 5 | T | T | T | F | T | T | T | T | F | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
3 | O |  |  |  |  | 9999 | Potchi | 50 | 2021-10-25 | 5 | F | T | T | T | T | F | T | T | T | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
4 | O |  |  |  |  | 111155 | Potchi | 50 | 2021-10-34 | 5 | F | T | T | F | T | F | T | T | F | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
5 | O |  |  |  |  | 99 | - | -88 | 100-22-55 | -5 | F | F | F | F | F | F | F | F | F | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
6 | O |  |  |  |  | 11155 | Potchi | -88 | 2021-10-12 | -100 | T | T | F | F | F | T | T | F | F | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
7 | O |  |  |  |  | 111111 | Potchi | 50 | 2021-10-25 | 5 | F | T | T | T | T | F | T | T | T | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
8 | O |  |  |  |  | 99999 | RedLobster | 5000 | 2021-10-25 | -1 | T | T | T | T | F | T | T | T | T | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
9 | O |  |  |  |  | 10001 | Toyo | -111 | 2021-10-25 | 5 | T | T | F | T | T | T | T | T | T | T | FAIL |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
10 | O |  |  |  |  | 10000 | Suka | 5 | 2021-10-25 | 5 | T | T | T | F | T | T | T | T | F | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
11 | O |  |  |  |  | 22435 | Patis | 10 | 10-2022-23 | 5 | T | T | T | F | T | T | T | T | F | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
12 | O |  |  |  |  | 88891 | Paminta | 33 | 23-2022-10 | 5 | T | T | T | F | T | T | T | T | F | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
13 | O |  |  |  |  | 10004 | PinkSalmon | 20 | 2021-10-25 | -100 | T | T | T | T | F | T | T | T | T | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
14 | O |  |  |  |  | - | - | - | - | - | F | F | F | F | F | F | F | F | F | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
15 | O |  |  |  |  | - | RebiscoBiscuit | 30 | 2021-10-25 | 5 | F | T | T | T | T | F | T | T | T | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
16 | O |  |  |  |  | 11111 | ChocoNut | - | 2021-10-25 | 5 | T | T | F | T | T | T | T | F | T | T | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
17 | O |  |  |  |  | 10088 | YahooChoco | 210 | - | 10 | T | T | T | T | T | T | T | T | F | T | FAIL |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
18 | O |  |  |  |  | 22255 | Vinegar200mL | 388 | 2021-10-25 | - | T | T | T | T | F | T | T | T | T | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
[6 empty] | ITEM ID |  |  |  |  | var....ITEM ID |  |  |  |  | var....ITEM ID ACTUAL
20 |  |  | O |  |  | 9999 | 10000 | 99998 | 99999 |  | F | T | F | F |  | F | T | F | F |  | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
21 |  | O |  |  |  | Invalid (9999) | Valid (10000-99999) | Invalid (99999-999999) |  | Invalid (<999999) | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
22 |  | O |  |  |  | -8 | 23555 | 999985 |  | 1111111 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
23 |  | O |  |  |  | -7 | 78787 | 999988 |  | 1222222 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
24 |  | O |  |  |  | -110 | 99991 | 999980 |  | 1333333 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
25 |  | O |  |  |  | -22 | 11235 | 999955 |  | 1444444 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
26 |  | O |  |  |  | -3 | 44567 | 999921 |  | 1555555 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
27 |  | O |  |  |  | -1 | 11155 | 999987 |  | 1000000 | F | T | F |  | F | F | T | F |  | F | PASS |  | J. Andicoy | 2021-10-28 | 951b1b1c6066e3f438e6147a0779c7aa39181f1a
Test Case # | Test Technique |  |  |  |  | INPUT |  |  |  |  | EXPECTED OUTPUT | [5 empty] | ACTUAL OUTPUT | [5 empty] | PASS/FAIL |  | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | ID string | DESCR string | QTY unsigned int | EXPIRY string | PRICE float | ID string | DESCR string | QTY unsigned int | EXPIRY string | PRICE float | MESSAGE string | ID string | DESCR string | QTY unsigned int | EXPIRY string | PRICE float | MESSAGE string
<Update Inventory Item>
1 | O |  |  |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 11 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
2 | O |  |  |  |  | 11101 | Kitkat (500g) | 180 | - | 11 | T | T | T | T | T | T | 11101 | Kitkat (500g) | 180 | - | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
3 | O |  |  |  |  | 10001 | Kitkat (50g) | 180 | 2022-01-01 | 11 | F | T | T | T | T | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 11 | NOT FOUND | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
4 | O |  |  |  |  | 11101 |  | 180 | 2022-01-01 | 11 | T | F | T | T | T | F | 11101 |  | 180 | 2022-01-01 | 11 | SUCCESS | FAIL |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee | Bug Report #: 6 Entering empty string into Description Field, will create a new line instead of accepting the empty string.
5 | O |  |  |  |  | 11101 | Kitkat (50g) | XXX | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | XXX | 2022-01-01 | 11 | INVALID | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
6 | O |  |  |  |  | 11101 | Kitkat (50g) | 180 | XXX | 11 | T | T | T | F | T | F | 11101 | Kitkat (50g) | 180 | XXX | 11 | INVALID | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
7 | O |  |  |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | XXX | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | XXX | INVALID | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
8 |  |  | O |  |  | 11101 | Kitkat (50g) | -1 | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | -1 | 2022-01-01 | 11 | INVALID | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
9 |  |  | O |  |  | 11101 | Kitkat (50g) | 0 | 2022-01-01 | 11 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 0 | 2022-01-01 | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
10 |  |  | O |  |  | 11101 | Kitkat (50g) | 1 | 2022-01-01 | 11 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 0 | 2022-01-01 | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
10 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | -0.1 | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | -0.1 | INVALID | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
11 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 0 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 0 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
12 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 0.1 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 0.1 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
13 |  |  | O |  |  | 11101 | Kitkat (50g) | 4999 | 2022-01-01 | 11 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 4999 | 2022-01-01 | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
14 |  |  | O |  |  | 11101 | Kitkat (50g) | 5000 | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | 5000 | 2022-01-01 | 11 | UPDATED | FAIL |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee | Bug Report #8 Input test data outside of boundary values still accepted
15 |  |  | O |  |  | 11101 | Kitkat (50g) | 5001 | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | 5001 | 2022-01-01 | 11 | UPDATED | FAIL |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
16 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 99999.99 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 99999.99 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
17 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000 | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000 | UPDATED | FAIL |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee | Bug Report #8 Input test data outside of boundary values still accepted
18 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000.1 | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000.1 | UPDATED | FAIL |  | J. Bandong | 2021-10-28 | 783ac1c0d4530b32576e390e1df5861d23aca2ee
19 |  |  | O |  |  | 11101 | Kitkat (50g) | 4999 | 2022-01-01 | 11 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 4999 | 2022-01-01 | 11 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
20 |  |  | O |  |  | 11101 | Kitkat (50g) | 5000 | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | 5000 | 2022-01-01 | 11 | INVALID | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
21 |  |  | O |  |  | 11101 | Kitkat (50g) | 5001 | 2022-01-01 | 11 | T | T | F | T | T | F | 11101 | Kitkat (50g) | 5001 | 2022-01-01 | 11 | INVALID | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
22 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 99999.99 | T | T | T | T | T | T | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 99999.99 | UPDATED | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
23 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000 | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000 | INVALID | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
24 |  |  | O |  |  | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000.1 | T | T | T | T | F | F | 11101 | Kitkat (50g) | 180 | 2022-01-01 | 100000.1 | INVALID | PASS |  | J. Bandong | 2021-10-28 | e494555b29e00f2bede883a369891bda4c7e6f68
Test Case | Test Technique |  |  |  |  | INPUT |  |  |  |  | EXPECTED OUTPUT |  |  |  |  | ACTUAL OUTPUT |  |  |  |  | PASS/FAIL |  | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | ID | DESCR | QTY | EXPIRY | PRICE | var1 | var2 | var3 | var4 | var5 | var1 | var2 | var3 | var4 | var5
<View Inventory List>
1 | O |  | O |  |  | 11101 | Nat. Spring | 200 | - | 16 | T | T | T | T | T | T | T | T | T | T | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
2 | O |  |  |  |  | aaa | Nat. Spring | 200 | - | 16 | F | T | T | T | T | F | T | T | T | T | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
3 | O |  |  |  |  | 11101 | 2222 | 200 | - | 16 | T | F | T | T | T | T | F | F | F | F | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
4 | O |  |  |  |  | 11101 | Nat. Spring | bbb | - | 16 | T | T | F | T | T | T | T | F | F | F | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
5 | O |  |  |  |  | 11101 | Nat. Spring | 200 | 2022-03-22 | 16 | T | T | T | F | T | T | T | T | T | T | FAIL |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
6 | O |  |  |  |  | 11101 | Nat. Spring | 200 | - | aaa | T | T | T | T | F | T | T | T | T | F | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
7 | O |  |  |  |  | MISSING CSV FILE |  |  |  |  | F | F | F | F | F | F | F | F | F | F | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
8 | O |  |  |  |  | WRONG FILE FORMAT |  |  |  |  | F | F | F | F | F | F | F | F | F | F | PASS |  | I. Paquibulan | 2021-10-28 | 9611efdf0cfaf3955369c5c4a2507d310ca6f21c
9
10
Test Case # | Test Technique |  |  |  |  | INPUT | EXPECTED OUTPUT | [6 empty] | ACTUAL OUTPUT | [6 empty] | PASS/FAIL | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | Item ID | Valid | Existing | Item ID | Description | Quantity | Expiry Date | Price | Valid | Existing | Item ID | Description | Quantity | Expiry Date | Price
<Search Inventory Item>
Note: " - " means not applicable
1 |  | o | o | o |  | 11113 | T | T | 11113 | SKyflakes | 23 | 30/05/2022 | 6 | T | T | 11113 | SKyflakes | 23 | 30/05/2022 | 6 | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
2 |  | o | o | o |  | 11107 | T | F | - | - | - | - | - | T | F | - | - | - | - | - | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
3 |  | o | o | o |  | -1 | F | - | - | - | - | - | - | F | - | - | - | - | - | - | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
4 |  | o | o | o |  | 100000 | F | - | - | - | - | - | - | F | - | - | - | - | - | - | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
5 |  |  |  | o |  | qwerty | F | - | - | - | - | - | - | F | - | - | - | - | - | - | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
6 |  |  |  | o |  | ABC123 | F | - | - | - | - | - | - | F | - | - | - | - | - | - | PASS | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c
7 |  |  |  | o |  | 123ABC | F | - | - | - | - | - | - | T | F | - | - | - | - | - | FAIL | JM. Marquita | 2021-10-29 | ad7a2514bae77110c87d668215cd757fb14fb55c | Bug report # 14
8
9
10
Test Case # | Test Technique |  |  |  |  | INPUT |  |  |  |  | EXPECTED OUTPUT |  |  | ACTUAL OUTPUT |  |  | PASS/FAIL | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | ID Number | Valid | Existing | Confirm Delete | Main Menu / Another ID | ID Number Deleted | ENTER Another ID | RETURN MAIN MENU | ID Number Deleted | ENTER Another ID | RETURN MAIN MENU
<Delete Inventory Item>
Note: " - " means not applicable
1 | o |  |  |  |  | 12101 | T | T | T | Another ID | DELETED | T | F | DELETED | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
2 | o |  |  |  |  | 12102 | T | F | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
3 | o |  |  |  |  | 12102 | T | F | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
4 | o |  |  |  |  | AAAAA | F | - | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
5 | o |  |  |  |  | AAAAA | F | - | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
6 | o |  |  |  |  | aaaaaa | F | - | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
7 | o |  |  |  |  | aaaaaa | F | - | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
8 | o |  | o |  |  | 100000 | F | - | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
9 | o |  | o |  |  | 100000 | F | - | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
10 | o |  | o |  |  | 9999 | F | - | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
11 | o |  | o |  |  | 9999 | F | - | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
12 | o |  |  |  |  | -12101 | F | - | - | Another ID | NOT FOUND | T | F | NOT FOUND | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
13 | o |  |  |  |  | -12101 | F | - | - | Main Menu | NOT FOUND | F | T | NOT FOUND | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
14 | o |  | o |  |  | 10000 | T | T | F | Main Menu | NOT DELETE | F | T | NOT DELETE | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
15 | o |  | o |  |  | 10000 | T | T | T | Another ID | DELETED | T | F | DELETED | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
16 | o |  | o |  |  | 99999 | T | T | F | Main Menu | NOT DELETE | F | T | NOT DELETE | F | T | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
17 | o |  | o |  |  | 99999 | T | T | T | Another ID | DELETED | T | F | DELETED | T | F | PASS | R.Manlangit | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
Test Case # | Test Technique |  |  |  |  | INPUT |  | EXPECTED OUTPUT |  | ACTUAL OUTPUT |  | PASS/FAIL |  | Executed By | Execution Date | Code Version | Comments (if any)
| MC/DC | EP | BVA | 0-Switch | C0/C1 | FILE | Function | FILE | OUTPUT | FILE | OUTPUT
<File Management>
1 |  |  |  |  | O | EXIST | START | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
2 |  |  |  |  | O | MISSING | START | CREATED | FILE CREATED | CREATED | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
3 |  |  |  |  | O | EXIST | ADD | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
4 |  |  |  |  | O | MISSING | ADD | CREATED | FILE CREATED | CREATED | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
5 |  |  |  |  | O | EXIST | UPDATE | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
6 |  |  |  |  | O | MISSING | UPDATE | CREATED | FILE CREATED | CREATED | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
7 |  |  |  |  | O | EXIST | VIEW | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
8 |  |  |  |  | O | MISSING | VIEW | CREATED | FILE CREATED | MISSING | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
9 |  |  |  |  | O | EXIST | SEARCH | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
10 |  |  |  |  | O | MISSING | SEARCH | CREATED | FILE CREATED | CREATED | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
11 |  |  |  |  | O | EXIST | DELETE | EXISTING | CONTINUE | EXISTING | CONTINUE | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad
12 |  |  |  |  | O | MISSING | DELETE | CREATED | FILE CREATED | CREATED | FILE CREATED | PASS |  | I. Paquibulan | 2021-10-29 | d9a1ea5cb88febedd8e7d9699593fd22977143ad

## Integration Testing
Integration Testing Test Cases
Project Name | Inventory System |  |  | Refer to this link for a sample of what to indicate as content in each column:
Module ID | INV-IT | Module Name | Use Case Scenario Testing | How to Write TEST CASES in Manual Testing ¦ Software Testing
Created By |  | Creation Date
Reviewed By |  | Review Date
|  | 20 | [6 empty] | Note: Do not indicate anything from this column onwards. (These columns are meant to record results of executing the test cases.)
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Procedure | Preconditions | Test Data | Post Conditions | Expected Result | Actual Result | Status | Executed By | Execution Date | Code Version | Comments (if any)
INV-IT-01 | Add Inventory Item: Main Success Scenario | INV-IT-01-01 | Addition of an inventory item that does not yet exist in the inventory file | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be added does not exist in the inventory file 3) The user has chosen "Add Inventory Item" menu option | 1) "INV-IT-01-01.csv" renamed as "Inventory.csv" 2) Test input data are as follows: ID : 11301 Description: Nat. Spring (4L) Quantity : 300 Exp. Date : 2021-10-29 Price (PHP): 40.35 | 1) The inventory file has a new inventory item. | 1) Message that the item is added into the inventory file is displayed on console. 2) Item inputted by staff is inserted into the appropriate position in the Inventory.csv file. | 1) Informs that the item has been successfully added. 2) Return to main menu. | PASS | J. ANDICOY | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT-01 | Add Inventory Item: 3b Error Scenario | INV-IT-01-02 | Addition of an inventory item using an invalid input | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be added has one or more invalid inputs 3) The user has chosen "Add Inventory Item" menu option | 1) "INV-IT-01-02.csv" renamed as "Inventory.csv" 2) Test input data are as follows: ID : Description: Nat. Spring (4L) Quantity : 300 Exp. Date : - Price (PHP): 40.35 | 1) The inventory file still has no new inventory item. | 1) Message that the item has not been added into the inventory file beacuse of an invalid input/s is displayed on console. | 1) Informs that there is an error due to an invalid input and the item is not added. 2) Return to main menu. | PASS | J. ANDICOY | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT-01 | Add Inventory Item: 4b Error Scenario | INV-IT-01-03 | Addition of an inventory item with an existing ID in the inventory fiel | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be added has an ID which is already existing inside the inventory file 3) The user has chosen "Add Inventory Item" menu option | 1) "INV-IT-01-03.csv" renamed as "Inventory.csv" 2) Test input data are as follows: ID : 11301* Description: Nat. Spring (4L) Quantity : 300 Exp. Date : - Price (PHP): 40.35 | 1) The inventory file still has no new inventory item. | 1) Message that the item has not been added into the inventory file because its ID is already existing is displayed on console. | 1) Informs that the item has been successfully added. 2) Return to main menu. | FAIL | J. ANDICOY | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT-02 | Update Inventory Item: Main Success Scenario | INV-IT-02-01 | Update of an inventory item that exists in the inventory file | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be updated has an ID which is already existing inside the inventory file 3) The user has chosen "Update Inventory Item" menu option | 1) Test input data are as follows: ID : 11101 Description: Nat. Spring (500mL) Quantity : 180 Exp. Date : 2022-01-01 Price (PHP): 11 | 1) The inventory file has updated the inventory item. | 1) Informs that the item has been updated. 2) Updates the inventory file. 3) Return to main menu | 1) Informs that the item has been updated. 2) Updates the inventory file. 3) Return to main menu | FAIL | J. BANDONG | 2021-11-01 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT-02 | Update Inventory Item: 1b Error Scenario | INV-IT-02-02 | Update of an inventory item that does not exist in the inventory file | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be updated does not exist in the inventory file 3) The user has chosen "Update Inventory Item" menu option | 1) Test input data are as follows: ID : 10001 Description: Nat. Spring (500mL) Quantity : 180 Exp. Date : 2022-01-01 Price (PHP): 11 | 1) The inventory file has not updated any inventory items. | 1) Informs that the item does not exist in the file. 2) Return to main menu | 1) Informs that the item does not exist in the file. 2) Return to main menu | PASS | J. BANDONG | 2021-11-01 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT-02 | Update Inventory Item: 6b Error Scenario | INV-IT-02-03 | Update of an inventory item that exists in the inventory file but has invalid field values. | 1) Input the test data on the console. 2) Confirm that the values to be added are correct. | 1) Inventory file exists 2) Inventory item to be updated exists in the inventory file 3) The user has chosen "Update Inventory Item" menu option | 1) Test input data are as follows: ID : 11101 Description: Nat. Spring Quantity : XXX Exp. Date : 2022-01-01 Price (PHP): XXX | 1) The inventory file has not updated any inventory items. | 1) Message that the item has not been updated in the inventory file because there are invalid values in the fields. 2) System prompts the user again for the correct values to be updated. 3) Return to main menu | 1) Message that the item has not been updated in the inventory file because there are invalid values in the fields. 2) System prompts the user again for the correct values to be updated. 3) Return to main menu | PASS | J. BANDONG | 2021-11-01 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT0-3 | View Inventory List | INV-IT-03-01 | Viewing all the items in the Inventory List | 1) Input the correct button on the console 2) It will be directed to the inventory list | 1) Complete details of every item exists | 1) Test input data are as follows: ID : 11301 Description: Nat. Spring (4L) Quantity : 300 Expiry Date : - Price (PHP): 40.35 | 1) The user viewed the inventory list | 1) Informs the staff viewed the inventory list. 2) Return to main menu | 1) Informs the staff viewed the inventory list. 2) Return to main menu | PASS | I. PAQUIBULAN | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT0-4 | Search Inventory List: Main success | INV-IT-04-01 | Searching the inventory if a particular item ID or product exists. | 1) Input test data. 2) Check if the test data is valid. 3) Check if the test data is existing. 4) Show the test data corresponding information. | 1) Inventory file exists. 2) The user has chosen "Search Inventory Item" menu option. 3) The inventory item must exist in the file for it to be found. | 1) Test input data are as follows: ID : 11101 | 1) The user will saw the displayed informations related to the test input. | 1) Information related to 11101. | Information related to 11101. | PASS | JM. MARQUITA | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT0-4 | Search Inventory List: 3b Error Scenario | INV-IT-04-02 | Searching the inventory for an item ID that doesn't exist. | 1) Input test data. 2) Check if the test data is valid. 3) Check if the test data is existing. 4) Show the test data corresponding information. | 1) Inventory file exists. 2) The user has chosen "Search Inventory Item" menu option. 3) The inventory item must exist in the file for it to be found. | 1) Test input data are as follows: ID : 11123 | 1) The system was not able to find the test data. | 1) Message to inform the user that the test data doesn't exist. 2) Message asking the user if wants to search again or go back to the main menu. | 1) Message to inform the user that the test data doesn't exist. 2) Message asking the user if wants to search again or go back to the main menu. | PASS | JM. MARQUITA | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77
INV-IT0-4 | Search Inventory List: 4b Error Scenario | INV-IT-04-03 | Searching the inventory for a invalid item ID that is not valid. | 1) Input test data. 2) Check if the test data is valid. 3) Check if the test data is existing. 4) Show the test data corresponding information. | 1) Inventory file exists. 2) The user has chosen "Search Inventory Item" menu option. 3) The inventory item must exist in the file for it to be found. | 1) Test input data are as follows: ID : ABC123 ID : 123ABC | 1) The system was not able to provide the information due to the invalid input. | 1) Message to inform the user that the test data is not valid. 2) Message asking the user if wants to search again or go back to the main menu. | 1) The message is "it doesn't exist", instead of "It's not valid". 2) Message asking the user if wants to search again or go back to the main menu. | FAIL | JM. MARQUITA | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77 | 1. Report bug for actual result #1. 2. Fixed
INV-IT0-4 | Search Inventory List: 5b Error Scenario | INV-IT-04-04 | Searching another inventory item after having previously searched one inventory item. | 1) Input test data. 2) Check if the test data is valid. 3) Check if the test data is existing. 4) Show the test data corresponding information. | 1) Inventory file exists. 2) The user has chosen "Search Inventory Item" menu option. 3) The inventory item must exist in the file for it to be found. | 1) Test input data are as follows: ID : 11101 ID : ABC123 ID : 123ABC | 1) The output will respond to the new input type, if it is valid or not. | 1) FOR VALID INPUTS: Information related to 11101. 2) FOR INVALID OUTPUTS: Message to inform the user that the test data is not valid. | 1) FOR VALID INPUTS: Information related to 11101. 2) FOR INVALID OUTPUTS: The message is "it doesn't exist", instead of "It's not valid". | FAIL | JM. MARQUITA | 2021-10-29 | 9097beb0c9cf44ea4df6aeb573d969402f58fb77 | 1. Report bug for actual result #2. 2. Fixed
INV-IT-05 | Delete Inventory Item: Main Success Scenario | INV-IT-05-01 | Deletion of an specific existing inventory item. | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted has the exact details of the item you want to be delete | 1) Inventory ID file number does exists 2) Inventory ID file number to be deleted does not exist in the inventory file 3) The user has chosen "Delete Inventory Item" menu option | 1) Deleted test data are as follows: ID : 11301 Description: Nat. Spring (4L) Quantity : 300 Exp. Date : - Price (PHP): 40.35 | 1) One inventory item has been removed in the inventory file | 1) Message that the selected item is deleted from the inventory file is displayed on console. 2) Item deleted by staff is removed from the Inventory.csv file. | "1) Message that the selected item is deleted from the inventory file is displayed on console. 2) Item deleted by staff is removed from the Inventory.csv file." | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 3b Error Scenario | INV-IT-05-02 | Deletion of inventory item using invalid input | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid | 1) Inventory ID file number inputted is invalid 2) The user has chosen "Delete Inventory Item" menu option | 1) Nothing changed | 1) Inform if the user wants to enter another inventory ID number 2) Inform if the user wants to return back to main menu | 1) Message that the inputted ID file number is invalid 2) Nothing changed in the Inventory.csv file." | 1) Message that the inputted ID file number is NOT FOUND 2) Nothing changed in the Inventory.csv file. 3) Will prompt the user if he/she wants to enter another data or return to main menu | FAIL | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744 | The system will check if the inputted ID Number is in the inventory.csv file or not, regardless if it is invalid or not. If inside the csv file, it will proceed to deleting, if not it will give a message "NOT FOUND"
INV-IT-05 | Delete Inventory Item: 3b Error Scenario Reenter another input ID | INV-IT-05-02-01 | Return to Reenter another input ID panel after inputting invalid input | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid | 1) Inventory ID file number inputted is invalid 2) The user has chosen "Delete Inventory Item" menu option 3) The user has chosen "Re enter another input ID" option | 1) Nothing changed | 1) The user will enter another input ID | 1) Displaying reenter delete input data panel 2) Nothing changed in the Inventory.csv file." | 1) The user can enter another Input ID 2) Nothing changed in the Inventory.csv file." | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 3b Error Scenario Return to Main Menu | INV-IT-05-02-02 | Return to Main Menu panel after inputting invalid input | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid | 1) Inventory ID file number inputted is invalid 2) The user has chosen "Delete Inventory Item" menu option 3) The user has chosen "Return to Main Menu" option | 1) Nothing changed | 1) The user is in the main menu | 1) Displaying Main Menu 2) Nothing changed in the Inventory.csv file." | 1) The user is now in the main menu panel 2) Nothing changed in the Inventory.csv file." | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 4b Error Scenario | INV-IT-05-03-01 | Deletion of inventory item using non-existing input ID | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid 3) Confirm that the test ID number inputted does not exists | 1) Inventory ID file number inputted does not exists 2) The user has chosen "Delete Inventory Item" menu option | 1) Nothing changed | 1) Inform if the user wants to enter another inventory ID number 2) Inform if the user wants to return back to main menu | 1) Message the user that the inputted ID file number does not exists 2) Nothing changed in the Inventory.csv | 1) Message the user that the inputted ID file number does not exists 2) Nothing changed in the Inventory.csv | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 4b Error Scenario Return to input ID Number | INV-IT-05-03-02 | Return to input data after using non-existing input ID | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid 3) Confirm that the test ID number inputted does not exists 4) Return to input ID | 1) Inventory ID file number inputted does not exists 2) The user has chosen "Delete Inventory Item" menu option | 1) Nothing changed | 1) The user will return to the panel where it will input again another ID file number | 1) Will prompt the user if he/she wants to go to input data panel or return to main menu 2) Nothing changed in the inventory.csv | 1) Will prompt the user if he/she wants to go to input data panel or return to main menu 2) Nothing changed in the inventory.csv | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 6b Error Scenario Not deleting inputted ID file number | INV-IT-05-04 | Not deleting the existing inputted ID file number | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid 3) Confirm that the test ID number inputted exists | 1) Inventory ID file number does exists 2) The user does not want to delete the data inside the inputted ID file number 3) The user has chosen "Delete Inventory Item" menu option | 1) Nothing Changed | 1) Inform if the user wants to enter another inventory ID number 2) Inform if the user wants to return back to main menu | 1) Nothing changed in the inventory.csv 2) Return to input data panel 3) Return to main menu | 1) Nothing changed in the inventory.csv 2) Return to input data panel 3) Return to main menu | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 6b Error Scenario Not deleting inputted ID file number -Return to input data | INV-IT-05-04-01 | Not deleting the existing inputted ID file number and returning to inputing data | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid 3) Confirm that the test ID number inputted exists 4) Return to Input data | 1) Inventory ID file number does exists 2) The user does not want to delete the data inside the inputted ID file number 3) The user want to input another ID file number 4) The user has chosen "Delete Inventory Item" menu option | 1) Nothing Changed | 1) The user will return to input ID file number menu | 1) Nothing changed in the inventory.csv 2) Return to input data panel | 1) Nothing changed in the inventory.csv 2) The user is now able to input another ID number | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744
INV-IT-05 | Delete Inventory Item: 6b Error Scenario Not deleting inputted ID file number -Return to main menu | INV-IT-05-04-02 | Not deleting the existing inputted ID file number and returning to main menu | 1) Input the test ID number on the console. 2) Confirm that the test ID number inputted is valid 3) Confirm that the test ID number inputted exists 4) Return to main menu | 1) Inventory ID file number does exists 2) The user does not want to delete the data inside the inputted ID file number 3) The user want to return to Main Menu 4) The user has chosen "Delete Inventory Item" menu option | 1) Nothing Changed | 1) The user will return to Main Menu | 1) Nothing changed in the inventory.csv 2) Return to main menu | 1) Nothing changed in the inventory.csv 2) The user has returned to Main Menu Panel | PASS | R. MANLANGIT | 2021-11-01 | ebed65b424c791924c1a99bfcba33f1764859744

## Time Log
Time Log
Instructions: Indicate the following data in your respective columns, as soon as you complete each lesson/topic
1) Completed on: date (format mm/dd/yyyy)
2) Time Spent (mins): total number of minutes spent to study the topic (example: "15", for 15 minutes)
3) Quality: Defect Removal Efficiency of the test activity -- please leave blank for now
Topic |  | M02 Joerenz |  |  | M03 Jupao |  |  | M11 Romz |  |  | M12 Maynard |  |  | M14 Ivan
Software Engineering Case Study/C Mini-Project |  | Completed on: | Time Spent (mins): | Quality: | Completed on: | Time Spent (mins): | Quality: | Completed on: | Time Spent (mins): | Quality: | Completed on: | Time Spent (mins): | Quality: | Completed on: | Time Spent (mins): | Quality:
|  | 2021-10-25 | 60 |  | 2021-10-25 | 60 |  | 2021-10-25 | 60 |  | 2021-10-25 | 60 |  | 2021-10-25 | 60
Requirements Analysis | 150 |  | 30 |  |  | 30 |  |  | 30 |  |  | 30 |  |  | 30
Understanding of Requirements Specifications | 75 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5
Documenting Assumptions & Clarifications | 75 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5
High-Level Design | 700 |  | 140 |  |  | 140 |  |  | 140 |  |  | 140 |  |  | 140
Use Case Description Creation | 300 | 2021-10-25 | 60 | 5 | 2021-10-25 | 60 | 5 | 2021-10-25 | 60 | 5 | 2021-10-25 | 60 | 5 | 2021-10-25 | 60 | 5
Screen Design Creation | 150 | 2021-10-25 | 30 | 5 | 2021-10-25 | 30 | 5 | 2021-10-25 | 30 | 5 | 2021-10-25 | 30 | 5 | 2021-10-25 | 30 | 5
High-Level Design Review | 100 | 2021-10-25 | 20 | 5 | 2021-10-25 | 20 | 5 | 2021-10-25 | 20 | 5 | 2021-10-25 | 20 | 5 | 2021-10-25 | 20 | 5
Use Case Description Correction | 75 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5
Screen Design Correction | 75 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5
Low-Level Design | 155 |  | 30 |  |  | 30 |  |  | 30 |  |  | 35 |  |  | 30
Flowchart Creation | 75 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-26 | 15 | 5 | 2021-10-25 | 15 | 5 | 2021-10-25 | 15 | 5
Flowchart Review | 50 | 2021-10-25 | 10 | 5 | 2021-10-25 | 10 | 5 | 2021-10-26 | 10 | 5 | 2021-10-25 | 10 | 5 | 2021-10-25 | 10 | 5
Flowchart Correction | 30 | 2021-10-25 | 5 | 5 | 2021-10-26 | 5 | 5 | 2021-10-26 | 5 | 5 | 2021-10-26 | 10 | 5 | 2021-10-26 | 5 | 5
Coding | 2605 |  | 685 |  |  | 480 |  |  | 480 |  |  | 480 |  |  | 480
Coding | 1600 | 2021-10-27 | 400 | 4 | 2021-10-27 | 300 | 5 | 2021-10-28 | 300 | 3 | 2021-10-28 | 300 | 3 | 2021-10-27 | 300 | 3
Code Review | 665 | 2021-10-29 | 185 | 4 | 2021-10-27 | 120 | 5 | 2021-10-28 | 120 | 3 | 2021-10-28 | 120 | 4 | 2021-10-27 | 120 | 3
Code Correction | 340 | 2021-10-30 | 100 | 4 | 2021-10-27 | 60 | 5 | 2021-10-28 | 60 | 4 | 2021-10-28 | 60 | 4 | 2021-10-27 | 60 | 4
Unit Testing | 2220 |  | 445 |  |  | 395 |  |  | 490 |  |  | 440 |  |  | 450
Unit Testing Test Case Design | 225 | 2021-10-26 | 45 | 4 | 2021-10-26 | 45 | 4 | 2021-10-26 | 45 | 4 | 2021-10-26 | 45 | 5 | 2021-10-26 | 45 | 4
Unit Testing Test Case Design Review | 100 | 2021-10-26 | 20 | 4 | 2021-10-26 | 20 | 5 | 2021-10-26 | 20 | 4 | 2021-10-26 | 20 | 5 | 2021-10-26 | 20 | 4
Unit Testing Test Case Correction | 150 | 2021-10-26 | 30 | 4 | 2021-10-26 | 30 | 5 | 2021-10-26 | 30 | 4 | 2021-10-26 | 30 | 5 | 2021-10-26 | 30 | 4
Unit Testing Execution | 285 | 2021-10-28 | 60 | 4 | 2021-10-28 | 60 | 5 | 2021-11-01 | 75 | 4 | 2021-10-29 | 45 | 5 | 2021-10-28 | 45 | 4
Unit Testing Test Results Review | 195 | 2021-10-28 | 30 | 4 | 2021-10-28 | 30 | 5 | 2021-11-01 | 35 | 5 | 2021-10-29 | 50 | 5 | 2021-10-28 | 50 | 4
Unit Testing Test Results Correction | 205 | 2021-10-30 | 50 | 4 | 2021-10-28 | 30 | 5 | 2021-11-01 | 45 | 5 | 2021-10-29 | 40 | 5 | 2021-10-28 | 40 | 4
Unit Testing Bug Fixing | 750 | 2021-10-30 | 150 | 4 | 2021-10-29 | 120 | 5 | 2021-11-01 | 180 | 4 | 2021-10-29 | 150 | 5 | 2021-10-29 | 150 | 4
Unit Testing Bug Fix Review | 160 | 2021-10-30 | 30 | 4 | 2021-10-29 | 30 | 5 | 2021-11-01 | 30 | 4 | 2021-10-29 | 30 | 5 | 2021-10-29 | 40 | 4
Unit Testing Bug Fix Correction | 150 | 2021-10-30 | 30 | 4 | 2021-10-29 | 30 | 5 | 2021-11-01 | 30 | 4 | 2021-10-29 | 30 | 5 | 2021-10-29 | 30 | 4
Integration Testing | 1700 |  | 390 |  |  | 330 |  |  | 310 |  |  | 340 |  |  | 330
Integration Testing Test Case Design | 150 | 2021-10-26 | 30 | 4 | 2021-10-26 | 30 | 4 | 2021-11-01 | 30 | 4 | 2021-10-26 | 30 | 5 | 2021-10-26 | 30 | 4
Integration Testing Test Case Design Review | 100 | 2021-10-26 | 20 | 4 | 2021-10-26 | 20 | 4 | 2021-11-01 | 20 | 4 | 2021-10-26 | 20 | 5 | 2021-10-26 | 20 | 4
Integration Testing Test Case Correction | 50 | 2021-10-26 | 10 | 4 | 2021-10-26 | 10 | 4 | 2021-11-01 | 10 | 4 | 2021-10-26 | 10 | 5 | 2021-10-26 | 10 | 4
Integration Testing Execution | 300 | 2021-10-29 | 60 | 4 | 2021-10-29 | 60 | 4 | 2021-11-01 | 60 | 4 | 2021-10-29 | 60 | 4 | 2021-10-29 | 60 | 4
Integration Testing Test Results Review | 160 | 2021-10-29 | 40 | 4 | 2021-10-29 | 30 | 4 | 2021-11-01 | 30 | 4 | 2021-10-29 | 30 | 4 | 2021-10-29 | 30 | 4
Integration Testing Test Results Correction | 170 | 2021-10-29 | 40 | 4 | 2021-10-29 | 30 | 4 | 2021-11-01 | 30 | 4 | 2021-10-29 | 40 | 4 | 2021-10-29 | 30 | 4
Integration Testing Bug Fixing | 325 | 2021-11-01 | 100 | 4 | 2021-11-01 | 60 | 5 | 2021-11-01 | 45 | 4 | 2021-10-29 | 60 | 4 | 2021-11-01 | 60 | 5
Integration Testing Bug Fix Review | 145 | 2021-11-01 | 30 | 4 | 2021-11-01 | 30 | 5 | 2021-11-01 | 25 | 5 | 2021-10-29 | 30 | 5 | 2021-11-01 | 30 | 5
Integration Testing Bug Fix Correction | 300 | 2021-11-01 | 60 | 4 | 2021-11-01 | 60 | 5 | 2021-11-01 | 60 | 4 | 2021-10-29 | 60 | 5 | 2021-11-01 | 60 | 4
Release | 1380 |  | 360 |  |  | 240 |  |  | 300 |  |  | 240 |  |  | 240
Software Release (for Integration Testing) | 340 | 2021-10-31 | 100 | 4 | 2021-10-29 | 60 | 5 | 2021-11-01 | 60 | 5 | 2021-10-29 | 60 | 5 | 2021-10-29 | 60 | 5
Software Release (for Acceptance Testing) | 740 | 2021-11-01 | 200 | 4 | 2021-11-01 | 120 | 5 | 2021-11-01 | 180 | 5 | 2021-11-01 | 120 | 5 | 2021-11-01 | 120 | 5
Software Release (for Final Release) | 300 | 2021-11-01 | 60 | 4 | 2021-11-01 | 60 | 5 | 2021-11-01 | 60 | 5 | 2021-11-01 | 60 | 5 | 2021-11-01 | 60 | 5
Acceptance Testing | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Acceptance Testing Bug Fixing | 0
Acceptance Testing Bug Fix Review | 0
Acceptance Testing Bug Fix Correction | 0